## Sheet1
ZONG CONTRACT 500 HOURS - PO NO. 048565 dated 30 July 2013
Document Ref | Hours Agreed | Running Balance | Start Date | Status | Live Date | Invoice Status | Invoice Date | Remarks
9 TAF Process | 24 | 476 |  | Delivered |  | Cleared | 2013-08-26
8 PO Line Auto Up dation & Confirmation Windows | 14 | 462 |  | Delivered |  | Cleared | 2013-09-04
11 PR, OPEX Report | 16 | 446 |  | Delivered |  | Cleared | 2013-09-23
13 BPMS Services (CMPak) Consolidated - PO OC | 97 | 349 |  | Delivered |  | Delivered/Pending | 2013-12-12 | Linked with 15
13 BPMS Services (CMPak) Consolidated - Forms | 32 | 317 |  | Delivered |  | Delivered/Pending | 2013-12-12
13 BPMS Services (CMPak) Consolidated - PR AC | 83 | 234 |  | Dev completed |  | Not Generated
14 Regional Changes in PR Process | 40 | 194 |  | Dev completed |  | Not Generated |  | Linked with 16
15 PO Cancellation | 32 | 162 |  | Delivered |  | Delivered/Pending | 2014-01-10
16 Regional Changes in PR Process | 56 | 106 |  | In progress |  | Not Generated
106
106
106
394