## Sheet1
ZONG CONTRACT 500 HOURS - PO NO. 048565 dated 30 July 2013
Sr. # | Document Ref | Hours Agreed | Running Balance | Start Date | Dev Status | Live Date | Invoice Status | Invoice Date | Remarks
1 | 9 TAF Process | 24 | 476 |  | Delivered |  | Cleared | 2013-08-26
2 | 8 PO Line Auto Up dation & Confirmation Windows | 14 | 462 |  | Delivered |  | Cleared | 2013-09-04
3 | 11 PR, OPEX Report | 16 | 446 |  | Delivered |  | Cleared | 2013-09-23
4 | 13 BPMS Services (CMPak) Consolidated - PO OC | 97 | 349 |  | Delivered |  | Delivered/Pending | 2013-12-12 | Linked with 15
5 | 13 BPMS Services (CMPak) Consolidated - Forms | 32 | 317 |  | Delivered |  | Delivered/Pending | 2014-01-27
6 | 13 BPMS Services (CMPak) Consolidated - PR Split & Return | 15 | 302 |  | Delivered |  | Delivered/Pending | 2013-12-12
7 | 13 BPMS Services (CMPak) Consolidated - PR Auto Cancellation | 68 | 234 |  | Dev completed as per initial requirement |  | Not Generated |  | End user will update after internal meeting to finalize changes.
8 | 14 Regional Changes in PR Process | 40 | 194 |  | Delivered |  | Delivered/Pending | 2014-01-27 | Linked with 16
9 | 15 PO Cancellation | 32 | 162 |  | Delivered |  | Delivered/Pending | 2014-01-10
10 | 16 Regional Changes in PR Process | 60 | 102 |  | Delivered |  | Delivered/Pending | 2014-01-27
11 | 17 Regional Changes in PR Process (Additional Req) | 24 | 78 |  | Delivered |  | Delivered/Pending | 2014-01-27 | Additional Req from user
12 | 18 PO Cancellation (New Changes) | 56 | 22 |  | Under Development (Delivery Date 7th Feb 2014) |  |  |  | Additional Req from user
13 | 17 Regional Changes in PR Process (PR flow changes) | 40 | -18 |  | Pending
518